## Fire Protection Except Pumps
PROJECT: SBL, MOHALI DATE:05/02/2025_FINAL
| TENTATIVE QTY. FOR HYDRANT, FOAM SPRINKLER AND COMPRESSED AIR PIPE AND MAJOR ITEMS Date:05.02.25 | [5 empty] | MAT STATUS as on 08.02.25 | SHORT FALL
SL.No. | ITEM | DESCRIPTION | UNIT |  | PH | TOTAL
1 | PIPE SIZE (GALVANIZED)
1.1 | 150NB | IS: 1239, Part-1 (HEAVY GRADE), GALVANIZED | RM | 1239 |  | 1239 | 1076 | -163
1.2 | 100NB |  | RM | 354 |  | 354 | 228 | -126
1.3 | 80NB |  | RM | 345 |  | 345 | 348 | 3
1.4 | 65NB |  | RM | 268 |  | 268 | 0 | -268
1.5 | 50NB |  | RM | 1629 |  | 1629 | 1464 | -165
1.6 | 40NB |  | RM | 1133 |  | 1133 | 546 | -587
1.7 | 32NB |  | RM | 742 |  | 742 | 546 | -196
1.8 | 25NB |  | RM | 783 |  | 783 | 0 | -783
1.9 | 25NB |  | RM | 4746 |  | 4746 | 4572 | -174
2 | PIPE SIZE (MS BLACK)
2.1 | 350NB | IS: 3589, 7MM THK. | RM | 48 | 30 | 48 |  | -48
2.2 | 300NB |  | RM | 6 | 3 | 6 |  | -6
2.3 | 250NB |  | RM | 36 | 48 | 48 |  | -48
2.4 | 200NB |  | RM | 2760 | 138 | 2760 | 2400 | -360
2.5 | 150NB | IS: 1239, Part-1 (HEAVY GRADE), MS BLACK, | RM | 408 | 1 | 408 |  | -408
2.6 | 100NB |  | RM | 186 | 6 | 186 |  | -186
2.7 | 80NB |  | RM | 33 | 12 | 33 | 36 | 3
2.8 | 50NB |  | RM |  | 48 | 48 |  | -48
2.9 | 40NB |  | RM |  | 12 | 12 |  | -12
2.1 | 25NB |  | RM | 45 | 18 | 48 |  | -48
3 | FOAM SPRINKLER NOZZLE K-42 ASPIRATION TYPE | AS PER APPROVED TDS | NOS. | 917 |  | 917 |  | -917
4 | SPRINKLER
4.1 | QBD_ UPRIGHT K-80,79° |  | NOS. | 957 |  | 957 |  | -957
4.2 | QBD_ UPRIGHT K-115,79° |  | NOS. | 40 |  | 40 |  | -40
4.3 | QBD_ PENDENT K-80,79° |  | NOS. | 431 |  | 431 |  | -431
5 | MVWS NOZZEL K-18,120° |  | NOS. | 254 |  | 254 |  | -254
6 | flexible drop (25NBX15NB) |  | NOS. | 177 |  | 177 |  | -177
7 | INSTALLATION CONTROL VALVE
7.1 | ICV-150NB |  | NOS. | 1 |  | 1 |  | -1
7.2 | ICV-100NB |  | NOS. | 3 |  | 3 |  | -3
7.3 | ICV-80NB |  | NOS. | 1 |  | 1 |  | -1
8 | DELUGE VALVE
8.1 | DV (150NB DRY TYPE) |  | NOS. | 19 |  | 19 |  | -19
8.2 | DV (100NB DRY TYPE) |  | NOS. | 4 |  | 4 |  | -4
8.3 | DV (80NB DRY TYPE) |  | NOS. | 1 |  | 1 |  | -1
8.4 | DV (80NB WET TYPE) |  | NOS. | 2 |  | 2 |  | -2
9 | BUTTERFLY VALVE
9.1 | BFV (200NB) |  | NOS. |  | 1 | 1 |  | -1
9.2 | BFV (150NB) |  | NOS. | 99 |  | 99 |  | -99
9.3 | BFV (100NB) |  | NOS. | 67 |  | 67 |  | -67
9.4 | BFV (80NB) |  | NOS. | 7 |  | 7 |  | -7
9.5 | BFV (65NB) |  | NOS. | 1 |  | 1 |  | -1
9.6 | BFV (50NB) |  | NOS. | 1 |  | 1 |  | -1
10 | GATE VALVES
10.1 | GATE VALVE (350NB) |  | NOS. | 1 |  | 1 |  | -1
10.2 | GATE VALVE (300NB) |  | NOS. | 2 |  | 2 |  | -2
10.3 | GATE VALVE (250NB) |  | NOS. | 3 |  | 3 |  | -3
10.4 | GATE VALVE (200NB) |  | NOS. | 27 | 1 | 28 |  | -28
10.5 | GATE VALVE (150NB) |  | NOS. | 29 |  | 29 |  | -29
10.6 | GATE VALVE (100NB) |  | NOS. | 9 |  | 9 |  | -9
10.7 | GATE VALVE (80NB) |  | NOS. | 6 |  | 6 |  | -6
11 | BALL VALVE
11.1 | 80NB (SS) Flanged End |  | NOS. | 5 |  | 5 |  | -5
11.2 | 50NB (SS) Flanged End |  | NOS. | 26 |  | 26 |  | -26
11.3 | 40NB (SS) Flanged End |  | NOS. | 1 |  | 1 |  | -1
11.4 | 25NB Screwed End |  | NOS. | 76 |  | 76 |  | -76
11.5 | 25NB Flanged End CL.-300# |  | NOS. | 2 |  | 2 |  | -2
12 | NON-RETURN VALVE
12.1 | NRV (350NB) Dual Plate Wafer Type -Del. Manifold |  | NOS. | 1 |  | 1 |  | -1
12.2 | NRV (200NB)Dual Plate Wafer Type -Fire Pump Delivery. |  | NOS. | 3 |  | 3 |  | -3
12.3 | NRV (150NB) Dual Plate Wafer Type (3 Nos. in Water Sprinkler System & 1 No. in Borewell) |  | NOS. | 4 |  | 4 |  | -4
12.4 | NRV (25NB) For Air Line Screwed End |  | NOS. | 46 |  | 46 |  | -46
12.5 | NRV (40NB) (SS) Wafer Plate Type |  | NOS. | 1 |  | 1 |  | -1
12.6 | NRV (50NB) (SS) Wafer Plate Type |  | NOS. | 24 |  | 24 |  | -24
12.7 | NRV (65NB) Wafer Plate Type |  | NOS. | 1 |  | 1 |  | -1
12.8 | NRV (80NB) Dual Plate Wafer Type - J.P.Delivery. |  | NOS. | 2 |  | 2 |  | -2
12.9 | NRV (80NB) Wafer Plate Type |  | NOS. | 22 |  | 22 |  | -22
12.1 | NRV (50NB) Wafer Plate Type |  | NOS. | 1 |  | 1 |  | -1
13 | Y-STRAINER
13.1 | YST (250NB) Fabricated with SS Elemant |  | NOS. | 3 |  | 3 |  | -3
13.2 | YST (150NB) Fabricated with SS Elemant |  | NOS. | 20 |  | 20 |  | -20
13.3 | YST (100NB) Fabricated with SS Elemant |  | NOS. | 6 |  | 6 |  | -6
13.4 | YST (80NB) Fabricated with SS Elemant |  | NOS. | 3 |  | 3 |  | -3
14 | HYDRAULICALLY OPERATED VALVE
14.1 | HOV (50NB) STD |  | NOS. | 22 |  | 22 |  | -22
14.2 | HOV (40NB) STD |  | NOS. | 4 |  | 4 |  | -4
15 | BLADDER TANK ( BARE-without Ratio Controller)
15.1 | CAP. 3500LTR. |  | NOS. | 3 |  | 3 |  | -3
15.2 | CAP. 3000LTR. |  | NOS. | 1 |  | 1 |  | -1
15.3 | CAP. 2500LTR. |  | NOS. | 1 |  | 1 |  | -1
15.4 | CAP. 2000LTR. |  | NOS. | 1 |  | 1 |  | -1
15.5 | CAP. 1000LTR. |  | NOS. | 1 |  | 1 |  | -1
16 | FLOW METER
16.1 | Flow meter 200nb |  | NOS. |  | 1 | 1 |  | -1
16.2 | Flow meter 100nb |  | NOS. |  | 1 | 1 |  | -1
17 | FLOW SWITCH Paddle Type,Honeywell |  | NOS. | 9 |  | 9 |  | -9
18 | FOAM PROPORTIONER
18.1 | FOAM PROPORTIONER (150NB) |  | NOS. | 18 |  | 18 |  | -18
18.2 | FOAM PROPORTIONER (100NB) |  | NOS. | 4 |  | 4 |  | -4
18.3 | FOAM PROPORTIONER (80NB) |  | NOS. | 3 |  | 3 |  | -3
19 | PRESSURE GAUGE
19.1 | PRESSURE GAUGE WITH Ball Valve |  | NOS. | 70 |  | 70 |  | -70
19.2 | PRESSURE SWITCH WITH Ball Valve |  | NOS. | 48 |  | 48 |  | -48
20 | Level Transmitter |  | NOS. | 2 |  | 2 |  | -2
21 | Flexible coupling Type Bellows 300NB |  | NOS. | 2 |  | 2 |  | -2
22 | AIR FILTER REGULATOR with Moisture Collection Trap (15NB) |  | NOS. | 23 |  | 23 |  | -23
23 | PRESSURE GAUGE
23.1 | PRESSURE RELIEF VALVE (INLET-150NB, OUTLET-250NB) |  | NOS. | 1 |  | 1 |  | -1
23.2 | PRESSURE RELIEF VALVE (INLET-25NB, OUTLET-40NB) |  | NOS. | 2 |  | 2 |  | -2
24 | COMPOUND GAUGE |  | NOS. | 3 |  | 3 |  | -3
25 | PRESSURE TRANSMITTER |  | NOS. | 2 |  | 2 |  | -2
26 | SOV Normally Closed,24V DC,FLP |  | NOS. | 25 |  | 25 |  | -25
27 | INTERNAL HYDRANT (SINGLE HEADED,Type-A) |  | NOS. | 19 |  | 19 |  | -19
28 | EXTERNAL HYDRANT (DOUBLE HEADED Comprising of 2 Nos Type-A Single Headed) |  | NOS. | 56 |  | 56 |  | -56
29 | HOSE BOX |  | NOS. | 47 |  | 47 |  | -47
30 | 15M HOSE |  | NOS. | 94 |  | 94 |  | -94
31 | BRANCH PIPE |  | NOS. | 94 |  | 94 |  | -94
32 | HOSE REEL |  | NOS. | 19 |  | 19 |  | -19
33 | STAND POST |  | NOS. | 28 |  | 28 |  | -28
34 | AIR RELEASE VALVE WITH PG |  | NOS. | 16 |  | 16 |  | -16
35 | FOAM WATER MONITOR (1750 LPM) |  | NOS. | 7 |  | 7 |  | -7
36 | 4 WAY FIRE BRIGADE CONNECTION with Internal NRV. |  | NOS. | 2 |  | 2 |  | -2
37 | MEDIUM EXPANSIO FOAM GENERATOR
37.1 | MEFG CAP-265LPM |  | NOS. | 4 |  | 4 |  | -4
37.1 | MEFG CAP-150LPM |  | NOS. | 4 |  | 4 |  | -4